|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Эмблема ERNAERNA - European Red Cross and Red Crescent Network on HIV, AIDS and TB**  **REPORT ON PLAN OF ACTION 2013** **Activities of the ERNA Secretariat**  1. Participation in the finalization of the PoA for ERNA 2013 (December 2012- January 2013) 2. Updating of the ERNA contacts 2013 (throughout the year 2013) 3. Participation in the ERNA Skype Board meetings (February 27, May 15, May 29, July 4, August 8) and face-to-face meeting on September 29 and composing the Minutes of the meeting in English and Russian. Posting all the ERNA Board Minutes on the ERNA website. 4. Communication with ERNA member National Societies and Partners (throughout the year 2013). 5. Communication with the Red Crescent Society of Tajikistan on the possibility of holding the 17th ERNA General Meeting in Dushanbe (Skype meetings, e-correspondence). 6. Preliminary visit of the ERNA Vice President and Coordinator to Dushanbe to select dates, venue of the meeting, meeting with the RC leaders and staff: appoint the working group from among the RC staff to be responsible for the GM organizational issues, examination of several options for social programme; finalization of the GM PoA and Grant Agreement; preparation of a draft GM Budget. 7. Preparatory work for the 17th ERNA General Meeting organization in cooperation with the Belarus RC staff, invitation of GM Guests (June-September 2013). 8. Preparation of documents and materials for ERNA General Meeting: sending invitations to ERNA member-NS leaders and contacts persons, dissemination of practical information, visa information, financial support application, and registration form). ERNA Coordinator concluded contracts with the hotel, the interpreters who participated in the GM, prepared the social event (excursion + gala dinner). 9. Preparation of printing materials to be put in folders and printing promotional materials, finalizing the agenda and list of participants in the GM. Organization of the GM Market Stall (July-September 2013). 10. The ERNA Secretariat assisted the GM participants both before the meeting (purchase of airtickets, visa support, practical advice) and after the meeting (reimbursement of the charges related to the participation in the GM). 11. Organization of the 17th ERNA General Meeting in Minsk, Belarus (27-29 September 2013). Taking minutes during the meeting. 12. Participation in the 17th ERNA General Meeting in Minsk, Belarus (27-29 September 2013) 13. Evaluation of the 17th ERNA General Meeting, English, Russian (October 2013). 14. Preparation of 17th ERNA GM Report in English and Russian (November-December 2013) 15. ERNA website maintenance: posting news and announcements, mailout of news; posting of photos, reports, articles. Translation of all the documents into Russian/English. 16. Analyzing the ERNA WS usability and creating a new updated WS layout based the needs of the visitors and a more contemporary vision. 17. Monitoring of the WS visits by means of Google Analytics. 18. Handover of the ERNA Secretariat activities to the Kyrgyz Red Crescent. Delegation of the ERNA Secretariat functions from the Belarus Red Cross 19. Opening of the separate ERNA Bank Account in Bishkek (December 2013). 20. Cooperation with the Kyrgyz RC in transferring the rest of funds from ERNA bank account in Minsk to the ERNA bank account in Bishkek. 21. Preparation of ERNA Financial and Narrative reports (throughout the year 2013) | | | | | | | | | |
|  |  | | | | | | | | | |
| **OBJECTIVES** | | | **ACTIVITY** | **INDICATORS/SUPPORTING DOCUMENTS** | **EXPENSES IN EUR** | **EXPENSES IN BYR (EUR EQUIV)** | **BUDGET / FINANCIAL PLAN** | | **BALANCE as of 20.12.2013** | | **RESULTS** | | |
| **[GOAL]**  **To contribute to the reduction of the spread of HIV, AIDS, TB and other communicable diseases principally among the most vulnerable people** | | |  |  |  |  | EUR 79.800,00 | |  | |  | | | |
| **[Outcome 1] –**  **To strengthen and promote the exchange of experiences, information and best practices among member National Societies and with others** | | |  |  |  |  | EUR 47.800,00 | |  | |  | | | |
| **[Output 1.1]** –  Exchange of experience and information and decision making sharing through the ERNA Board  *February 2013*  *(electronically done)* | | | Agenda points/contents to be defined during the Board Meeting:  - Adopting of the previous meeting minutes  - Analysing of 2012 PoA and budget  - Up-dating over Budget 2013  - Finalizing of the ERNA Plan of Action 2013  - Response from the RCS of Tajikistan hosting the 17th General Meeting; analysis of offer for location proposed by RCS of Tajikistan  - Definition of the GM theme  - Analysis of the NSs feedback regarding possible annual membership contribution  - Discussion of fundraising from internal and external donors | Budget for 2013 up-dated  PoA for 2013 finalized after got back comments from Member NSs  Location for ERNA 17th  annual General Meeting (GM) defined. Draft MoU between ERNA and RCS of Tajikistan hosting 17th GM prepared. Budget of the meeting discussed.  Minutes of ERNA Board meetings published over the ERNA website |  |  | Included in General Administration Cost (see Annex 1 for ERNA Budget 2013 in EUR)  No expenses for travel and accommodation as it is done electronically | |  | | ERNA Board meeting electronically done – in Skype format on February, 27, 2013  - All issues considered and solved. ERNA Board meeting Minutes posted on the ERNA website  Output is fully reached | | | |
| **[Output 1.2] –**  Exchange of experience and information sharing through the ERNA Board meeting | | | Participation of the full Board (President, Vice-presidents, ERNA General Coordinator, RCS of Tajikistan representative, IFRC, Youth ECC and PLHIV representatives)  - Adopting the minutes from the previous meeting  - Preparations of the 17th ERNA General Meeting:  \* Discussing the *draft ToR of the GM (prepared by ERNA Board with the assistance of IFRC)*, its objectives and criteria for attendance and participation by members  \* Discussion MoU with the host NS  \* Outline the Agenda of the General Meeting  \* Preparing topics and list of the guests to be invited for the 17th ERNA General Meeting discussed  \* Preparing and sending out invitations to RCRC and external partners (end of May-June)  \* Forming and agreeing upon the working group for ERNA GM 2013  \* Discussing possibilities and facilities to organize the GM  \* Discussing the promoting materials on ERNA GM  \* Discussing the budget of the GM  - ERNA Secretariat elections  - Current ERNA budget 2013 | - Agenda of the AGM and work in groups are agreed upon.  - Provisional Programs are adopted.  - Provisional list of the guests are approved.  - Details are agreed upon  - Budget of the meeting is defined.  - ERNA Secretariat budget report shared.  - Venue of the meeting is approved.  - Agenda of the meeting and work in groups is agreed upon.  Report published over the ERNA website |  |  | EUR 5.000,00  No expenses for travel and accommodation as it is done electronically | | EUR 5.000,00 | | - ERNA Board meeting electronically done – in Skype format on May, 13 and 29  - All issues considered and solved. ERNA Board meeting Minutes posted on the ERNA website  17th ERNA GM theme is defined – “Vulnerable migrants’ access to HIV and TB services”  Output is fully reached | | | |
| **[Output 1.3] -** Consultations of ERNA Board and ERNA Secretariat with the host NS for the 17th ERNA General Meeting  *June 2013* | | | ERNA President (Vice-President) and ERNA Secretariat Coordinator preparatory visit to the GM location in Tajikistan and organizational issues | Agreements on the budget are agreed with host NS  Meeting with the government representatives carried on | 885 | 1,348,66 | EUR 3000,00 | | 766,34 | | ERNA President (Vice-President) and ERNA Secretariat Coordinator preparatory visit to the GM location in Tajikistan and organizational issues  Output is fully reached | | | |
| **[Output 1.4] -**  Exchange of experience and information and decision making sharing through the ERNA Board  *July and August 2013 (electronically done)* | | | Discussing the results of preparatory visit to the RCS of Tajikistan | Report from the ERNA Secretariat Coordinator preparatory visit to the GM location in Tajikistan and the report from the Tajik RC on the GM preparations |  |  | Included in General Administration Cost (see Annex 1) | |  | | - Two ERNA Board meetings electronically done – in Skype format ( 4 July, 8 August 2012)  - All issues considered and solved. ERNA Board meeting  GM goal, main tasks defined, Agenda drafted. Minutes posted on the ERNA website  Output is fully reached | | | | |
| **[Output 1.5] -**  Sharing experiences and best practices of member National Societies during the annual ERNA General Meeting  *September 2013* | | | 17th ERNA Annual General Meeting well organized and executed: theme and sessions chosen respecting needs of the hosting NS; Member NSs and reliable Partners included in the preparation of sessions; NSs presenters selected according to best practice they developed in the topic.  Workshops by interactive methods of work widely used  Active role played by external stakeholders ( PLHIV, International and National Organizations)  Best practices sharing among member National Societies  Active participation in the ERNA Secretariat election process | Hosting NS representative participated in the GM decisional making process at the Board  N. of sessions prepared following this principle  N. of NSs involved  N. of Partners involved  No. of Member NSs represented  Interactive participation of all concerned members in the sessions    Key elements shared on specific issues discussed in the sessions  Key elements extracted from the outcome of the workshops.  Reinforced partnership with other involved stakeholders  Participants actively involved in the workshops and discussions.  ERNA Secretariat for the three years mandate elected  Rate of participants who filled the evaluation questionnaire  Full Report published over the ERNA website | 3.382,05 | 27,175 | EUR 35.000,00  Full accommodation and travel costs for ERNA GM supported NSs and guests, translation, rent of meeting premises, stationary and printing, support for fuel expenses  Travel of the elected President and Vice-President covered by their respective NSs | | 4.442,95 | | -17th ERNA GM “Vulnerable migrants’ access to HIV and TB services”: HIV and TB” organized.  -21 RCRC National Societies, 11 partner organizations and IFRC representatives participated in the 17th ERNA General Meeting (70 participants: 55 representatives of NSs and partner organizations, 6 volunteers, 9 BRCS supporting staff members)  -Best practices included in Agenda for sharing among member National Societies  -Workshops with interactive methods of work held for wide use during the meeting  -Active participation of ERNA partners during the meeting provided  -Organization of the Board election process carried on.  -ERNA President and Vice-president elected  - 29 out of 44 representatives of NSs and RC/RC partner organizations filled out the evaluation questionnaire  Output is fully reached | | | |
| **[Output 1.6] -** Verification and accountability of the ERNA member key contact person as adherence to the requirements in the ToR to Member NSs on their Key tasks and responsibilities (Annex 2 of the ToR adopted by the GM on 2010 in Minsk) | | | Contact with each Member NS to constantly up-date their contact person  Share relevant information with key contact people  Permanent consultation over relevant themes done electronically | Key ERNA Member NSs contact list constantly up-date  Number of positive feed-backs received from key contact persons regarding NSs actions, plans relevant to ERNA mission such as PoA, Strategy 2012-2013, revised ToR, etc. |  |  | Included in General Administration Cost (see Annex 1) | |  | | -Contact information concerning all the ERNA member NSs, IFRC Geneva, IFRC EZ, IFRC Regional Representations, ERNA partners updated regularly within a year  -All Internet possibilities used actively for distribution materials and sharing information by the ERNA Secretariat  12 ERNA contact persons sent their feedback to update “NSs activities” section on the ERNA website. Contact persons from NSs of Serbia, Kazakhstan, Kyrgyzstan, Croatia, Belarus, Montenegro, Bosnia and Herzegovina, Moldova, Latvia updated their NS contacts and activities. Swedish, Danish and Spanish RCs informed that their NSs do not implement any HIV/TB related projects.  Output is fully reached | | | |
| **[Output 1.7]** –  Exchange of experience and information sharing through the ERNA Board meeting | | | The ERNA Board welcomes a new ERNA Secretariat which accepts mandate from the previous one for the next three years  - Adopting the previous ERNA Board meeting minutes  - Adopting the Report of the 17th ERNA General Meeting  - Discussing the Evaluation of of the 17th ERNA GM  - Discussing the Strategic Plan for ERNA 2014-2015  - Discussing the ERNA PoA 2014  - Discussing ERNA budget 2014  - Current ERNA budget 2013 | Draft Report of the 17th ERNA General Meeting  List of Board members suggestions  ERNA Secretariat budget report  ERNA PoA and budget for 2014 |  |  | EUR 3.000,00  Travel of the elected President and Vice-President covered by respective NS | 3.000,00 | | | -ERNA elected a new Board during the 17th ERNA GM  -Board held right after the GM  -ERNA Board meeting Minutes posted on the ERNA website  Output is fully reached | | |
| **[Output 1.8]** -  To strengthen the ERNA network and the relation with relevant stakeholders through the exchange of experience and information by the website | | | -Updating the website on the regular basis in two languages  -To insert relevant information from member National Societies and relevant stakeholders  - To keep working with ERNA website interactive part | N. of news posted  N. of electronic advices offered  N. of visits to the website  N. of PLHIV organizations using the platform as its own  N. of other stakeholders linked |  | 11,62 | EUR 1.800,00  for the web site maintenance | 1,788,38 | | | ERNA website (WS) updated on the regular basis. Relevant information from member National Societies and relevant stakeholders inserted.  15 news, 17 announcements , 18 documents for the Library posted on the WS and distributed among the NSs and partners  -ERNA Pages on Twitter, Flickr, You Tube mantained  -ERNA Facebook Group has reached 115 Members of 29 different NSs, IFRC, ICRC and other stakeholders. 130 News posted  -ERNA is represented in Wikipedia  -ERNA Google Analytics account maintained  -N. of website visits  2013: = n.a.  -N. of PLHIV organizations using the platform as their own  in 2013 = 3  -N. of other stakeholders linked  in 2013 = 12  Output is fully reached | | |
| **[Output 1.9] –**  To make a simple communication strategy both for internal (membership) and external (partners and stakeholders)use, that includes a commitment to routine periodic communication and makes clear what is expected in response (from members)  **[Output 1.10] –**  Tomake a plan to engage in a more strategic way with NS leadership to improve ‘buy-in’ and continuity of commitment to ERNA membership and participation | | | A simple communication strategy used while keeping in touch with ERNA members and partners.  Developing draft ERNA Communication Strategy on the basis of practical experience (by ERNA Board with the assistance of the IFRC)  Discussing and adopting the Strategy during the 17th ERNA GM  - Development of the ERNA Plan of action 2013.  - Approval of the Plan of action by the ERNA member NSs leadership  - The Plan of action 2013 posted on the ERNA website.  - The performance of the plan monitored by the ERNA Board | Internal and external communication daily maintained.  A draft communication strategy developed  The Strategic PoA 2013 adopted, sent to NSs and posted on the ERNA website.  N. of discussions between the leadership of ERNA member National Societies and ERNA Board, Secretariat  in 2013 = |  |  | Included in General Administration Cost (see Annex 1)  Included in General Administration Cost (see Annex 1 ) |  | | | Output is fully reached | | |
| **[Outcome 2] –**  **To promote the setting up of innovative initiatives and to reproduce them in other National Societies by adapting them to the beneficiaries** | | |  |  |  |  | Included in General Administration Cost (see Annex 1) | |  | |  | | |
| **[Output 2.1]** –  Increase of visibility on activities developed in the field of Harm Reduction, HIV, AIDS and TB programmes run by NSs  *March 2013* | | | Report on the Questionnaire for member NSs about activities and achievements in the field of Harm Reduction, HIV, AIDS and TB  It has to be done by ERNA Secretariat in cooperation with the Board  Mapping results of activities Disseminating the information | N. of persons answering the questionnaire  N. of trained persons  N. of new HR, HIV, AIDS, TB programs/projects in member National Societies  Sustainability of ( N.) current programs /projects run by member National Societies  published over the ERNA website |  |  |  | |  | | Questionnaire on HR, HIV /TB, drug issues, achievements of the 19 representatives from 7 NSs and one Partner Organization who participated in the trainings in Villa Maraini (includes activities on advocacy/fighting stigma and discrimination/humanitarian diplomacy) prepared and disseminated among the ERNA member NSs.  Output partially reached | | |
| **[Output 2.2] –**  Increase Visibility on ERNA Network  *Throughout 2013* | | | To disseminate informational ERNA Booklet, ERNA/IFRC Newsletter devoted ERNA and other promotion materials through every meetings, communications with internal and external stakeholders | N. of disseminated promotional materials (segregated by type)  News published over the ERNA website |  |  |  | |  | | ERNA Booklet distributed in English and Russian (over 100 English booklets and 150 Russian booklets)  -IFRC EZ Newsletter dedicated to ERNA distributed electronically and by post by the IFRC EZ office  -Important news published over the ERNA website (about ERNA member NSs activities, Villa Maraini partnership on substance abuse, Regional Health Initiative for Eurasia, World TB Day, World AIDS Day)  Output partially reached | | |
| **[Output 2.3] –**  Develop a monitoring and evaluation framework which will include key performance indicators and a systematic way to capture lesson learning and promote good practice  *July-August 2013* | | | Developing monitoring and evaluation framework by the ERNA Board with the assistance of the IFRC | A draft framework prepared  N. of NSs which submitted their amendments and supplements to the draft framework.  The framework adopted by the ERNA Board, disseminated among the member NSs and posted on the ERNA website.  Monitoring results disseminated among NSs and posted on the ERNA website. |  |  |  | |  | | In Progress  Output partially reached | | |
| **[Outcome 3] –**  **To promote and facilitate concerted collaborative actions in the prevention of HIV, AIDS, TB and other communicable diseases with UN agencies, EU, non-governmental organizations, Global Fund and other international and national organizations and with existing Federation’s Networks** | | |  |  |  |  | EUR 10.000,00 | |  | |  | | |
| **-[Output 3.1] –**  Strategic partnership between National Societies and other agencies & partners  *Partners to be invited to the 17th ERNA General Meeting* | | | -Increasing the existing cooperation with UNAIDS, WHO, UNODC, EU, Global Fund, Stop TB, HRI, AAE and other Civil Society Organizations  -To seek for other potential partners/donors involved in the field of HIV/AIDS, TB and other communicable diseases. | Number of partnership established – communication with member NSs on this regard  Participation of ERNA Board member at relevant Meetings organized by external potential partner organizations |  |  | EUR 3.000,00  If possible partners will pay for their own participation | | 3.000,00 | | 12 NSs presented information concerning their HIV/TB projects supported by RC donor NSs: Italian RC, Spanish RC, American RC, French RC, Norwegian RC, German RC), Global Fund in partnership with Regional Health Initiative for Eurasia, (Resource centre in Irkutsk, Russia), STOP TB Partnership,  Output partially reached | | |
| **[Output 3.2] –** Strengthen Partnership within the RC/RC Movement and other RC/RC Networks on HIV and TB | | | - Increase number of ERNA members  - Joint participation of ERNA, ART, EYN and other IFRC networks in the international events, meetings, trainings  - Share information of ART and other IFRC networks through ERNA website  - To share information /and make available space on ERNA website for the HIV/TB IFRC networks from other regions (outside Europe) | Participation of ERNA Board members at relevant meetings, trainings, events  New experience, know-how and ideas shared through minutes, reports and website |  |  | EUR 3.000,00  Travel of the ERNA President covered by his NS | | 3.000,00 | | -Communications with European RCNSs performed in order to disseminate ERNA best practices and in order to increase number of ERNA members.  Danish RC resigned its Membership as ERNA Member  -Joint participation in International meetings ERNA/ART  -Participation of the ERNA President at the ART workshop on HR and ART Annual Meeting in Lao, January 2013  Output partially reached | | |
| **[Output 3.3] -**  Building partnership in Harm Reduction activities, events, initiatives. | | | To increase cooperation with international organizations on harm reduction | Participation of ERNA Board members at relevant events, meetings, trainings  New experience, know-how and ideas shared through minutes & reports and ERNA website |  |  | EUR 3.000,00 | | 3.000,00 | | ERNA Board and Secretariat improved collaboration with HRI and EHRN  Output partially reached | | |
| **-[Output 3.4] –**  Strategic partnership between ERNA, and other IFRC Networks established or improved  *Throughout 2013* | | | To establish cooperation with, PERCO, Psychological Support, First Aids network and with the new entity established among IFRC/ItRC/Villa Maraini named “The Red Cross Red Crescent Training and Research Partnership on Substance Abuse” | N. of exchanges with the three networks and with the “Partnership..” |  |  | Included in General Administration Cost (see Annex 1) | |  | | -Efforts to establish cooperation with PERCO, Psychological Support, First Aids Network are being made  -the ERNA President designated as coordinator of the “Partnership..”  Output not yet reached | | |
| **[Output 3.5] -** Maintaining good cooperation with IFRC/RC Europe Zone  Cooperation with the Red Cross EU Office based in Brussels | | | Europe Zone Health representative participating at ERNA Boards and General meetings  Partnership with the RC/EU Office,  RC EU Office representative present at ERNA AGM - presenting possible calls for proposals | Increased exchange of information with the IFRC Europe Zone office  Number of options for applications presented |  |  | Budget covered by IFRC representatives | |  | | -IFRC and Europe Zone Health representatives participate at ERNA Boards and General meetings. Partnership with the RC/EU Office is established  Output is fully reached | | |
| **[Output 3.6] –**  Starting cooperation with European Funding Practitioners Group (EFPG)  *Throughout 2013* | | | ERNA Board member participates in the EFPG meetings |  |  |  | EUR 500,00 | | 500,00 | | Output not yet reached | | |
| **[Output 3.7] –**  Starting cooperation with American Red Cross  *Throughout 2013* | | | Cooperation on organization joint events, trainings, study visits to the ERNA member NSs, information exchange, improving the functioning of ERNA website | N. of events/meetings organized  N. of study visits  N. of trainings  N. of information exchanged, including via website  Increased positive statistics in the ERNA website analytics reports |  |  | EUR 500,00 | | 500,00 | |  | | |
| **[Outcome 4] –**  **To strengthen PLHIV in better raise their voice and their capacity to develop their role in the community** | | |  |  |  |  | EUR 7.000,00 | |  | |  | |
| **[Output 4.1] –**  **Reinforce and/or build new partnerships with PLHIV NGO’s in order to expand existing actions and to promote new initiatives at all levels**  *Throughout 2013* | | | General assessment of actors involved in the field:  - identification of PLHIV organizations, relevant NGO’s, and groups at national and local level;  - establishing of bilateral dialogue.  Acting together for:  - a multilateral understanding of each player by exposing their overall activities;  - identifying a shared agenda of priorities and activities;  - sharing responsibilities among the players by activities | N. of meetings organized and  N. of relevant stakeholders involved  Increased cooperation of National Societies and national PLHIV organizations:  N. of NGOs included in partnership through common agenda (MoU, Consensus statements, etc) |  |  | EUR 3.000,00 | | 3.000,00 | | **-**ERNA member NSs established and developed cooperation with national PLHIV organizations.  - ERNA increased cooperation with GNP+, Aids Action Europe, East Europe and Central Asia Union of PLHIV/All Ukranian Network of PLHIV  Output is fully reached | | |
| **[Output 4.2] - Partnership and more involvement of PLHIV and other target groups in ERNA activities in ERNA General Meetings** | | | GNP+ and PLHIV/TB representatives are invited as special reliable partners at the annual ERNA GM | Relevant contributions of GNP+ and/or PLHIV/TB representatives assured during the GM  N. of speeches and presentations held by such partners  GM-2013 = |  |  | EUR 4.000,00 | | 4.000,00 | | -PLHIV representatives actively involved to the ERNA General Meeting (2 representatives of international organizations ( and 2 representatives of Belarusian PLHIV)  Output is fully reached | | |
| **[Output 4.3] –**  **Involving the PLHIV in the ERNA governance**  *September 2013,*  *at the 17th ERNA GM* | | | PLHIV special advisor/representative for ERNA Board to be selected for two years: 2014-2015 | PLHIV representative participates at the ERNA Board Meetings  PLHIV presence at the ERNA Board get visibility through the ERNA web site  Development of a practice that can be proposed as good practice advocating for more inclusion of beneficiary communities in the Governance of RC/RC bodies |  |  | The cost is included in the budget line of the Board Meetings | |  | | Ms. Elena Grigoryeva, Chair of Aids Action Europe, Belarusian PLHIV community contributed actively to the activity of the Network as special advisor for the ERNA Board.  The changing of the composition of the Board and of the location of the Secretariat will led to re-discuss this issue later on  Output partially reached | | | | |
| **[Output 4.4] –**  **To promote the role of PLHIV organizations in evaluation of projects targeted to vulnerable people** | | | To collect and disseminate the existing best practices  RC NSs regularly involve positive people to response to HIV, AIDS and TB at the national and local level | N. of evaluations done  N. of people from among vulnerable communities who were actively involved in the RC activities at the national and local level in 2013 – to be done through a Eng & Rus questionnaire to be sent to ERNA Member NSs |  |  | Included in General Administration Cost (see Annex 1) | |  | | ERNA Secretariat collects and disseminates the existing best practices  Output is partially reached | | | | |
| **[Output 4.5] –**  **To promote better awareness over the stigma affecting PLHIV** | | | In Partnership with PLHIV referral Org. (GNP+) ERNA will promote the adoption of the “STIGMA INDEX” via ERNA website | ERNA website present the information |  |  | Included in General Administration Cost (see Annex 1) | |  | |  | | | | |
| **[Outcome 5] –**  **To build capacity on Humanitarian Diplomacy to apply in the field of HIV and TB together with Member NSs.** | | |  |  |  |  | Included in General Administration Cost (see Annex 1) | |  | |  | | | | |
| **[Output 5.1] –**  **Using appropriate tools on Humanitarian Diplomacy (HD) on HIV and TB**  *Throughout 2013* | | | Disseminating and promoting IFRC HD Manual Guide (?) and the “course on-line on HD” | Number of situations where the tool has been used  Number of courses executed |  |  | Included in General Administration Cost (see Annex 1) | |  | | -Specific part of ERNA website with HD materials opened  - Professional “Humanitarian Diplomacy Guidance Series” are being prepared by IFRC and will be disseminated among the NSs as soon as it will be edited  - The developing of tools on HD will be promoted  Output partially reached | | | | |
| **[Output 5.2] – Strengthening partnership with WHO**  *Throughout 2013* | | | Invite WHO for 17th ERNA GM  To cooperate with WHO for a specific action in specific country as expressed by NSs | N. of RCRC projects were WHO is partner  N. of informational documents shared between WHO and ERNA on the field of HIV/TB |  |  | WHO should finance participation in the 17th ERNA GM | |  | | -Due to financial situation the representative of WHO can’t participate in the 17th ERNA GM  - Cooperation with WHO for a specific actions in specific countries performed  Output partially reached | | | | |
| **[Outcome 6] –**  **National Societies in countries in transition and developing countries improve their capabilities in being relevant stakeholders in the Region through common projects of European National Societies** | | |  |  |  |  | EUR 13.000,00 | |  | |  | | | | | |
| **[Output 6.1] –**  **Focusing and sharing of best practices**  *Throughout 2013* | | | To support financially the participation of some member NS at special events related to HIV, TB and other communicable diseases | N. of National Societies which participated in international conferences presenting best practices or in specific trainings |  |  | EUR 3.000,00 | | 3.000,00 | | -Best practices shared through ERNA website. Financial support of some member NS at special events related to HIV, TB and other communicable diseases will be provided if there are enough ERNA funds  Output not reached | | | | |
| **[Output 6.2] –**  **Raising skills in project implementation**  *Throughout 2013* | | | To find possibilities for facilitating exchange/study visits among member National Societies, exchange of experiences from each other | N. of exchange/study/cooperation visits done  Report of the event results  Report disseminated through ERNA website |  |  | EUR 10.000,00 | | | 10.000,00 | -Conditions will be created for facilitating exchange/study visits among member National Societies, exchange of experiences from each other – if there are enough ERNA funds  Output not yet reached | | |
| **[Output 6.3] –**  **Increase number of projects of HIV, AIDS and TB co-funded by EU funds or from other external donors**  *Throughout 2013* | | | To use the expertise of IFRC Europe Zone and expert National Societies in preparing projects proposals to external donors.  To use the Villa Maraini experts and the IFRC Partnership on Substance Abuse as a reference tool for harm reduction projects | N. of projects prepared to external donors |  |  | Included in General Administration Cost (see Annex 1) | | |  | -Conditions will be created for facilitating exchange/study visits among member National Societies, exchange of experiences from each other – if there are enough of ERNA funds  Output is not yet reached | | |
| **[Outcome 7] –**  **To promote the integration of HIV, AIDS, TB and other communicable diseases into other health programs** | | |  |  |  |  | EUR 2.000,00 | | |  |  | | |
| **[Output 7.1**] **-**  **Increase of awareness and best practices among RCRC NSs and Governmental Institutions**  *Throughout 2013* | | | At the 17th ERNA General Meeting invites Governmental Institutions of hosting NSs presenting HIV, AIDS and TB related activities done in collaboration with RCRC NSs and vice-versa | Meetings organized  No. of presentations in which is explained the cooperation between Government and RC |  |  | EUR 2.000,00  Plus costs for supporting the participation at the GM are included in that budget | | | 2.000,00 |  | | |
| **Expenses on the ERNA General Meeting in 2011 (reimbursement of expenses)** | | |  |  | 656,12 |  |  | | |  |  | | |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | | |  | | |  |  | | |  |  | | |
| **ANNEX 1 FOR ERNA Budget 2013 in EUR** | | | | | |  |
| **PERSONNEL AND GENERAL ADMINISTRATION** | | | | | |  |
| **PERSONNEL** | | | | | |  |  | | |  |  | | |
|  | | | | | |  | 9342,78 | | | EUR 12.916,00 | 3573,22 | | |
| Salary costs ERNA coordinator (800 EUR x 12) + social fund contributions | | | | | |  |  | | |  |
|  | | | | | |  | 1047,03 | | |  | 1858,97 | | |
| Salary costs coordinator assistant (180 EUR x 12) + social fund contributions | | | | | |  |  | | | EUR 2.906,00 |
|  | | | | | |  |  | | | **Sub Total** 15.822,00 |  | | |
| **GENERAL ADMINISTRATION** | | | | | |  |  | | |  |  | | |
| Phone and fax | | | | | |  | 1,18 | | | 300 | 298,82 | | |
| Stationery (including paper, seal/stamps…) | | | | | |  | 33,64 | | | 440 | 406,36 | | |
| Internet | | | | | |  | 66,33 | | | 120 | 53,67 | | |
| Postage | | | | | |  | 25,6 | | | 200 | 173,5 | | |
| Representation costs | | | | | |  | 12,00 | | | 600 | 588 | | |
| Banking charges | | | | | |  | 59,11 | | | 900 | 509,3 | | |
| Foreign exchange differences | | | | | |  |  | | | 1,020 | 1020 | | |
| Book keeping costs (190 EUR x 12) + social fund contributions | | | | | |  | 2298,42 | | | 3,068 | 769,58 | | |
| General reserve | | | | | |  |  | | | 5,500 | 5,500 | | |
|  | | | | | |  |  | | | **Sub Total** 12.148,00 |  | | |
|  | | | | | |  |  | | | **Total**  **EUR 27,970,00** |  | | |
|  | | | | | | | | | | | | | | | |  |
|  |  |  | | |  | | |  | | | |
|  | | | |
| **BUDGET ACCORDING TO THE PLAN OF ACTION 2013** | | | | | |  |  | | | **EUR, 79,800,00** |  | | |
| **PERSONNEL AND GENERAL ADMINISTRATION** | | | | | |  |  | | | **EUR, 27.970, 00** |  | | |
| **TOTAL** | | | | | | **5,254,76** | **41,422,27** | | | **EUR, 107,700,00** | **61,749,09** | | |
|  | | | | | |  |  | | | | | | | |
| **BALANCE in EUR 20.12.2013** | | | | **30,461,36** | | | | |  | | | | | | | |
|  | | | | Transferred to the Kyrgyz RCS bank account on  24.12.2013 | | | | | * 30,461,36 EUR | | | |  | | |
| **BALANCE in BYR on 20.12.2013** | | | | **0** | | | | |  | | | | | | | |
|  | | | |  | | | | |  | | | |  | | |
|  | | | |  | | | | |  | | | | | | | |
|  |  |  | | |  | | |  | | | |