ERNA – European Red Cross / Red Crescent Network on HIV/AIDS

## Plan of Action 2002

# Background

ERNA was established in 1997 in Rome with the aim of coordinating the sharing of experiences, transfer of best practices and the promotion of collaborative efforts among NSs of the European region.

The networks vision is to have well functioning National Societies that are able to address HIV/AIDS and related problems.

The mission of the network is to strengthen National Societies operational capacity to combat HIV/AIDS by gradually developing activities at the community level particularly in the areas of prevention, control, psychosocial support, social integration and other community activities targeted at the most vulnerable people.

# General objective of ERNA

To prevent the spread of HIV/AIDS, principally among the most vulnerable population.

### Plan of Action 2002

| Specific objectives outlined in the TORs for ERNA | Specific activities for 2002 | Expected results | Indicators | Assumptions | Time frame | Budget / financial plan |
| --- | --- | --- | --- | --- | --- | --- |
| To create or strengthen the existing system for the promotion of exchange of experiences, information and best practices among member national societies and with others to enable them to intensify their efforts in the fight against HIV/AIDS | Meeting of the Bureau of ERNA in Rome. The IFRC Secretariat will be also invited. ERNA and IFRC RD Budapest to be represented at the International Harm Reduction Conference ERNA Secretariat to be represented at the Berlin Conference Presentation of mapping of the HIV situation in Europe, done in collaboration with RD Budapest Preparatory visit at the Armenian RC for the 6th ERNA meeting To participate at the 14th International AIDS Conference in Barcelona Side-event panel discussion with ENP+ and other potential partners To arrange the 6th ERNA meeting in Yerevan, Armenia, devoted to harm-reduction, including workshop on harm reduction. | Agreement for proceeding of the Network until the next elections in 2003 Partnership Support member NSs Promotion of ERNA and its activities in the region Attracting new members from Europe Verify and check all the possibilities and facilities to organize the annual meeting Partnership enhanced Support of ERNA members Organizational matters, review on functioning of the Network Agreement on PoA 2003 and budget for 2003 | Well-functioning Network, which will be a tool for member NSs in HIV/AIDS prevention Endorsed PoA New members attracted to ERNA Support got from PNSs Successful presentation Cooperation with Armenian RC and support in preparatory works Well organized side-event Increased number of partners Follow-up of the youth-peer education Implementation of existing projects Modification of TOR from organizational and administrative point of view To have elected the second Vice-President | That ERNA is invited to Berlin That there are funds to organize the meeting That there are candidates for the post of the 2nd Vice-President | 14-17 March 2002 Ljubljana, 3-7 March 2002 April 14-19, 2002 June 2002 July 7-12, 2002 September 2002 | Bureau members and invitees (4+2) Travel – 10 000 CHF Accommodation and Board to be covered by the Italian RC Other participants (IFRC Secretariat) cover the travel/accommodation expenses by themselves President of ERNA and IFRC RD Health delegate pay all related costs themselves 3 persons x 2000 CHF – 6000 CHF President of ERNA paid from own NS 2 persons x 2500 CHF = 5000 CHF President of ERNA will cover his expenses by own Side-event to be organized by the IFRC Secretariat 2x1500 CHF = 3000 CHF President of ERNA paid from own NS 50 000 CHF |
| To promote the setting up of innovative initiatives and to reproduce them in other national societies by adapting them to the beneficiaries specificity | Continue to link NSs project proposals with potential donors Based on proposals from NSs and ERNA leadership, create a European Strategic Plan of Action for European NSs members on HIV/AIDS prevention To produce information materials, training material on Harm reduction, materials for promoting ERNA (T-shirts, leaflets, brochures, cards, etc.) to be given out on special occasions such as meetings, conferences, etc. To keep the ERNA website updated all the time, insert new information from member NSs To establish a Harm Reduction trainig Center at Villa Maraini Foundation, Italy Organize a training course on Harm reduction | Increased capacity of member NSs More action by NS to prevent the epidemic To better reach specific target groups with HIV prevention More effective sharing of experiences and knowledge Easier for NSs to start prevention programs when training material exists Information tool for members Capacity building and knowledge sharing of members - “ - | That the pilot projects that find assistance run well and are able to show progress Training material produced Leaflets distributed at he Berlin Conference Regular feed-backs from members about all HIV related activities within their NS Well trained persons from member NS | That the pilot projects will be financially covered and that there will be sufficient funds for them That it will “sell” the project proposals of member NS and will help to cover them financially That the projects will be implemented That member NSs are willing to be part of one strategic plan That it serves as an information tool for members and other interested parties That Italian RC supports this idea That there are enough interested persons and experienced trainers/educators | Progress report on financed projects at the 6th ERNA meeting By the end of 2002 Leaflets to be produced before April 2002 Throughout 2002 By the end of 2002 During 2002 | Some projects to be financed through member PNSs and others with assistance or through RD Budapest 5000 CHF –consultants; administrative costs Leaflets – 2500 CHF Cards – 1500 CHF Training materials = 10000 CHF at the first stage (printing and drafting group) To be covered by RD Budapest (3000 CHF) To be determined To be determined |
| To promote and facilitate concerted collaborative actions in the prevention of HIV/AIDS with UN agencies, EU, other international and national organizations and with existing Federation’s Networks | Increase the existing cooperation with ENP+ and GNP+, UNAIDS, WHO, EU, etc. To seek for other potential partners/donors involved in the fight against HIV/AIDS Anti-stigma campaign in collaboration with RD Budapest | Strategic partnership between NSs and other agencies & partners Establish partnership with PLWHA Global awareness for people about the rights and lives of PLWHA | That NSs have started taking contact with partners and that they see the need and benefit of Strategic Partnership and working with other organizations That the society will get appropriate information about PLWHA and change attitudes and reduce prejudices towards PLWHA | That NSs have programs and projects to present and to offer to potential partners That RC becomes a safe place for PLWHA That there is an acceptance from people to learn about PLWHA and to accept the diversity | Throughout 2002; new partners to be invited to the 6th ERNA meeting in September 2002 May 2002 | Partners will pay for their own participation in general and ERNA will cover costs for specially invited guests from e.g PLWHA – 5000 CHF Provided by RD Budapest |
| To give technical support and assistance to member NSs (upon expressed need) in areas where a gap in knowledge and skill exists with the motive of fostering their operational capabilities | Based on evaluation of the workshop from 5th ERNA meeting, to arrange a project planning process (PPP) workshop for member NSs / max. 20 people Computer and language (French) training for ERNA Secretariat coordinator, upgrade of PC of the ERNA Secretariat | NSs able to create good projects acceptable to donors Better working possibilities in the day-to-day administrative work | That NSs are able to attract donors and partners Active participation in PPP workshop Increased capacity of admin. working duties | That there is financial and technical possibility to organize such workshop That there will be enough interested NSs to participate That there are funds for it | October 21-25 place to be determined 1st half of 2002 French course throughout 2002 | ERNA/RD 25000 CHF RD will provide facilitators ERNA Computer – 180 CHF French – 240 CHF PC upgrade – 1000 CHF |
| To render technical support and assistance to NSs in countries in transition and developing countries through common projects of European NSs | To be able to cover financially participation for member NS to conferences related to the problematic of HIV (limited number – “first ask=first served”) To facilitate exchange visits among member NS, exchange of experiences from one to other, especially among countries in transition/PNSs | Increased information among members Exchange of knowledge among members, better possibilities to have more effective programs, information sharing | Acquired knowledge included in NSs projects Active involvement of all concerned members | That member NSs express their concrete needs, wishes and proposals for such study visits That there are sufficient funds for it That NSs will benefit from such visits | Throughout the year 2002 continuous | 4000 CHF 3000 CHF |
| To promote the integration of HIV/AIDS into other health programs and develop tools and methods for its implementation | At the 6th ERNA meeting an expert from Croatian RC (eventually also from other member NS) will share experience in harm reduction | Increased knowledge in member NSs | Presentation of those NSs that have experience in harm reduction | That there will be a NSs wanting to share its experience | September 2002 | See budget for the 6th ERNA meeting |
| To emphasize the gender perspectives in all interventions. | Information sought from ART task force 2000 that has a specific session on gender issues Contact with IFRC Secretariat GVA Gender officer will be made for advise on how to fulfill this objective | Increased knowledge about the issue | Information collected | That other Network share their experience | During 2002 | No specific costs required |

| Budget for secretariat administration for 2002 : Salary of program coordinator (including social insurance) Internet Stationary Post and phone expenses | 1089 CHF/month = 13068 CHF/year 473 CHF 125 CHF 982 CHF/month = 11 788 CHF/year |
| --- | --- |

| Total budget ERNA 2002 | CHF 156 874 |
| --- | --- |