ERNA – European Red Cross / Red Crescent Network on HIV, AIDS and TB

## Plan of Action 2010

# ERNA background

ERNA was established in 1998 in Rome with the aim of coordinating the sharing of experiences, transfer of best practices and the promotion of collaborative efforts among National Societies of the European region. The network’s vision is to have well functioning National Societies that are able to address HIV, AIDS, TB and related problems. Currently ERNA gathers 40 Red Cross and Red Crescent Societies from Europe.

The mission of the network is to encourage participation and to help strengthen National Societies' operational capacity to combat HIV, AIDS, TB and other communicable diseases by gradually developing activities at the community level particularly in the areas of prevention, care, treatment, control, harm reduction, psychosocial support, legal support, reduction of stigma and discrimination, social integration and other community activities targeted at the most vulnerable people.

# General objective of ERNA is to contribute to the reduction of the spread of HIV, AIDS, TB and other communicable diseases principally among the most vulnerable people.

ERNA is taking a lead role in promoting the links between National Societies and networks and other organisations. It is a coordinating body searching for better communication between National Societies as well as between National Societies and the Federation. ERNA has an important role in strengthening advocacy activities. ERNA in its work supports HIV and AIDS Global Alliance in European region as well as its main objectives:

- preventing further infections

- expanding care, treatment and services

- reduce stigma and discrimination

- strengthening community

The link with TB Survival Project , relevant  PLWH Organisations , Central and Eastern European Harm Reduction Network (CEEHRN), IFRC networks , will be reinforced and more practical work with them will be initiated.

# ERNA is strongly supporting sharing of the expertise done in the field of humanitarian treatment of drug users, including comprehensive harm reduction approach. The Italian Red Cross is very well working on it providing to Sister National Societies trainings in Rome at Villa Maraini, and supporting National Societies who are ready to start actions in their own countries . Similarly, ERNA would like to discover and share the very good experience that some NS has already got in the field of fighting stigma and discrimination towards people living with diseases  .  The aim is to present  and promote the already existing very good experiences that needs to be shared within the Movement.

The Network envisages the follow-up discussions between the Villa Maraini experts, National Societies, the IFRC Health and Care Department , the Europe Zone and Rome Consensus in order to identify current challenges in the field of Harm Reduction.

Following the discussion from  Tallinn (2007) and Belgrade (2008)  about greater involvement of the youth in ERNA functioning, ERNA Board proposed to co-opt a youth representative to ERNA Board meetings in 2009.  During ERNA conference in Kyrgyzstan (2009) ECC membership was approved by Annual Meeting in Kyrgyzstan  and  institutionally regulated  in ERNA  ToR .  For 2010 similar solution is proposed for PHLW diseases organizations .

ERNA is aiming to spreading knowledge through Training of Trainers for Project Planning Process in order to improve NSs capacity building in the field of external financing.

Two NS’s  proposed in written to host of the 14th ERNA meeting, for the year  2010. : Belarus  Red Cross ,and  Slovenian  Red Cross. Georgia Red Cross also reconfirmed the commitment to host the conference when full stability in the country is gained . Through common sharing and analyses among the three partners ERNA Board gets the result that Belarus will host the 2010 GM and Slovenia the 2011 one.

Plan of Action for ERNA 2010

| Specific objectives outlined in the TORs for ERNA | Specific activities for 2010 | Expected results | Indicators | Assumptions | Time frame | Budget / financial plan |
| --- | --- | --- | --- | --- | --- | --- |
| To strengthen and promote the exchange of experiences, information and best practices among member National Societies and with others | ERNA Board Meeting Youth representative co-opted ERNA Board Meeting Consultations of ERNA Secretariat with the host NS for the 14th ERNA meeting ERNA Board meeting in Budapest To organize the 14th ERNA meeting ERNA Board Meeting | Analyses of 2009 plan and budget Drafts of the ERNA PoA 2010 and its Budget Proposals for hosting 144h Annual meeting .Mechanism to co-opt PLW org . - level to be defined . Selection of the host Preparations of the 14th ERNA meeting - preparation of topics List of the guests to invite for the 14th ERNA meeting discussed Working group for ERNA Annual Meeting 2010 formed Possibilities and facilities to organize the annual meeting discussed Promoting materials on ERNA Annual Meeting discussed. Preparation and further discussions on the 14th ERNA meeting Hosting NS defined, meeting and MoU with the host NS prepared and signed Visit of ERNA Secretariat Coordinator to Minsk Agenda of the meeting outlined Working groups agreed Budget of the meeting approved MoU with the host NS signed. …Analyses with IFRC Zone further improvement in cooperation with ERNA… Facilitated knowledge and experience sharing Main theme focused on de-stigmatization, “Empowering vulnerable people in fighting stigmatization and discrimination” 14th ERNA Meeting evaluation | Budget for 2010 and Plan of Action for 2010 drafted Provisional Programs for 14th ERNA Meeting adopted Provisional list of the guests approved Details agreed upon Venue of the meeting approved Budget of the meeting discussed Agenda of the meeting and work in groups agreed upon Agreements on the budget agreed with host NS Member National Societies shared their experience at the Conference Reinforced partnership with other involved stakeholders Active participation of all concerned members in the sessions Increased knowledge among member NS on specific issues discussed in the sessions Best practices shared among the member National Societies | Host NS provides necessary information and cooperates in ERNA Meeting preparatory works with ERNA Secretariat The budget for the meeting is covered. The budget for supporting the participation of NSs requesting support is covered That National Societies are willing to report on their best practices That there are available lecturers and facilitators for the workshops That the member National Societies participate actively in the workshops | December 2009 Belgrade , Serbia February 2010 Spring 2010 Late Spring 2010 September 2010. Late autumn 2010 | Travel (partially), meals and accommodation expenses for participants partially covered by ERNA budget 3000 Travel, (partially), meals and accommodation expenses for Board meeting covered by ERNA budget 3000 3000 Travel (partially), meals and accommodation expenses for Board meeting covered by ERNA budget 3000 The budget for 14 th Annual meeting (incl. travel (partially), expenses, meals and accommodation) covered by ERNA budget Its cost will be 51000 ( including PLW communities, ECC, special guests expenses) Travel (partially), meals and accommodation expenses for Board meeting covered by ERNA budget 3000 |
| To promote the setting up of innovative initiatives and to reproduce them in other National Societies by adapting them to the beneficiaries | Follow-up of Harm reduction training courses in Villa Maraini – sharing experiences with NSs. Questionnaire about achievements to be produced by ERNA Secretariat . Cooperation with IFRC Health and Care department in Geneva and Zones Mapping on NSs activities on HIV /TB , harm reduction and drug issues (includes activities on advocacy / fighting stigma and discrimination ) To keep ERNA website updated all the time, insert the relevant information from member National Societies To make ERNA web site interactive with additional Q&A page | Extended sharing of experience with other partners Capacity building and knowledge sharing of members in the field of Harm Reduction Information tool for members More effective sharing of experience and knowledge leading to better HIV, AIDS programmes on NS level. Sharing information, Exchange of knowledge among members, better possibilities to reach directly and at the same time more stakeholders | Well trained persons and sustainable HR programes/projects in member National Societies Feedback from members about activities done in the field of drug use Feedback from members about activities done in the field of HIV, AIDS and TB and other communicable diseases Well-informed members, Good knowledge about the members and their activities | That the NSs express their interest to follow-up That the NSs continue to carry out Harm Reduction activities That there are experts available to provide the follow-up That this mapping action will be actively networking supported by some Key person to be identified in some key NS That there is an interest to use interactive discussion | Throughout 2010 Throughout 2010 and continuously Throughout 2010 and continuously | No additional expenses (covered by ERNA Secretariat) No additional expenses To be discussed on ERNA Board and with members 300 |
| To promote and facilitate concerted collaborative actions in the prevention of HIV, AIDS, TB and other communicable diseases with UN agencies, EU, non-governmental organizations, Global Fund (to fight AIDS, TB and Malaria),other international and national organizations and with existing Federation’s Networks | Increase the existing cooperation with ENP+ and GNP+, UNAIDS, WHO, UNODC, EU, Global Fund, Stop TB, and other Civil Society Organizations. To seek for other potential partners/donors involved in the fight against HIV, AIDS, TB and other communicable diseases . To increase cooperation with PERCO network as migrants are among most vulnerable To explore for cooperation with existing IFRC networks on HIV and TB . To explore cooperation with European PS network: stigma, the theme for the 2010 AM, is a common topic To liaise with and PLW organizations Meeting of ERNA President with representatives of relevant PLW organizations Participation of ERNA President to the European RC/RC Conference and ECM Youth Meeting in Vienna Participation of ERNA distinguished member ( Secretary General of the NS) to the Global Alliance Meeting close to AIDS conference and his presentation of activities Maintaining good cooperation with Europe Zone Cooperation with the Red Cross EU Office based in Brussels | Strategic partnership between National Societies and other agencies & partners Partnership in Harm Reduction activities, events, initiatives Partnership between ERNA and PLW organizations discussed and agreed upon , PLW representative for ERNA Board selected Strengthening Partnership within the RC Movement Strengthening partnerships and visibility Europe Zone Health representative participating at ERNA Boards and General meetings Partnership with the RC/EU Office. RC EU Office representative present at Annual ERNA meetings - presenting possible calls for proposals | Number of partnership established – communication with member NSs Participation of Erna President and Vice-Presidents at relevant Meetings organized by external potential partner organizations Increase in assistance Increase in assistance | That National Societies have programmes and feasible projects to present and to offer to potential partners, that there is a will to cooperate. To explore if there is possibility to include Potential Partners’ tools in our actions That there is a reciprocal interest in cooperation Good practices shared That there is a reciprocal interest in cooperation HIV and TB projects available at EU level | Throughout 2010 Partners to be invited to the 14th ERNA annual meeting Throughout 2010details to be determined Throughout 2010; details to be determined April 2010 July 2010 | Partners will pay for their own participation in general Erna President and Vice-Presidents Travels possibly hosted or covered by their respective National Society Accommodation, travel of ERNA President covered by ERNA budget 1500 Accommodation, travel of ERNA President covered by ERNA budget 2500 Participation covered by National Society |
| To involve PLW in work at all levels | To establish contact and initiate the partnership with relevant PLW organizations To maintain partnership with TB Survival Project To invite PLW, and other affected people and their NGOs to 14th Annual Meeting | Partnership in activities at all levels Partnership and more involvement of PLW and other target groups in ERNA activities | Increased cooperation of National Societies and national PLW organisations | That there is a reciprocal interest in cooperation That there is a reciprocal interest in cooperation | Throughout 2010 Throughout 2010 | ERNA covering necessary costs of the invited persons for 2010 annual meeting (The cost is included in the budget line of the GA) |
| To render technical support and assistance to National Societies in countries in transition and developing countries through common projects of European National Societies | To create conditions for covering financially participation of some member NS at special events related to HIV and other communicable diseases To launch a competition among member NSs to select the winner., according to criteria of best practices and highest needs To ask support from possible donor to gain the fund for the winner To try to create conditions for facilitating exchange/study visits among member National Societies, exchange of experiences from one to other, especially among countries in transition NSs Use the expertise of IFRC Europe Zone and National Societies successful in preparing projects proposals to external donors . ERNA will promote the growing of expertise in NSs in preparing project proposals to external donors through targeted training for planning process | Visibility and share of NS’s best practices Exchange of knowledge among members, better possibilities to have more effective programmes, information sharing Successful and effective HIV, AIDS and TB projects co-funded by EU funds To improve NSs capacity in the field of external financing through trained people | Number of National Societies which participated in international conferences Number of applications received Improvement in the quality of project organization and implementation by involved National Societies N. of exchange/study visits done Number of Public projects accepted by external donors N. of Training for Project Planning Process Managers N. of trained people N. of RC National Societies involved in the process | That member National Societies express their concrete needs, wishes and proposals for such study visits That there are sufficient funds for it That there are sufficient funds for it That National Societies will benefit from such visits That National Societies have well trained staff and sufficient funds in order to be capable to submit project proposals to external donors That the project Planning Capacity is needed by NSs Sustainable Funding | 2010/2011 2010/2011 2010/2011 December 2010 | Fund to be covered by new donor Fund to be covered by new donor No fund needed EUR 14.000 for travel expenses covered by ERNA . New donor needed to assist to organize additional travel and administrative expenses for this meeting Foundation Von Goethe will host the participants and trainers for free Strasbourg RC Branch will support with transportation |
| To promote the integration of HIV, AIDS, TB and other communicable diseases into other health programmes and develop tools and methods for its implementation . | To invite one or more experts from member National Societies to share their experience (co-operation with Ministry of Health – Social support and Health education) At the 14th ERNA Meeting invited UN agencies representatives presenting HIV, AIDS and TB related activities done in collaboration with Governments and RC/RC NSs | Increased knowledge Spread of helpful information and well-tried practices, know-how Increased cooperation between RCRC / International and Governmental Institutions | Number of such presentation done | That these experiences do exist and need to be shared | During the 14th Meeting |  |